# Accessibility Allies Draft Plan

## Suggested schedule for Accessibility Allies.

2pm daily catch up (informal), with a member of DL staff in on M, W, F (after the first week): TS, MD, JA, JL, SB, AR to rotate, so it is 15 minutes once a fortnight.

| Week number and date | Meetings | Synchronous training | Asynchronous training | Main tasks |
| --- | --- | --- | --- | --- |
| 1 | Introduction to other interns Introduction to DL team + Dave. (Org chart so they know who’s who.) Introduction to ADE/DHoSE for the faculty they will be working with | Introduction to Blackboard (get a sandbox set up for them) Introduction to Blackboard Ally Word training session | Mandatory Health and safety stuff MS Accessibility fundamentals (2.5 hours) AbilityNet course | Finding Word docs and remediating them Do AbilityNet course and write up some feedback. |
| 2 | Introduction to Enabling Services | PowerPoint training session | Creating accessible documents in Word and Adobe Acrobat (10 hours) –LiL pathway Enhance DTP accessibility module (1/11) |  |
| 3 | Introduction to CHEP/inclusive education workstream |  | UDL (Universal Design for Learning) online resources (Bb course) Accessible colours (UDLHE Digicon presentation) Alt text – CoP (Community of Practice) presentation Enhance DTP accessibility module (2/11) |  |
| 4 | Introduction to OneWeb (perhaps ask them to give a brief talk?) | Editing captions in Panopto, Stream and YouTube (SB/Media Team) | Enhance DTP accessibility module (3/11) |  |
| 5 |  |  | Enhance DTP accessibility module (4/11) |  |
| 6 |  | What is a VPAT? | Enhance DTP accessibility module (5/11) |  |
| 7 | Introduction to ECS Accessibility Team |  | Enhance DTP accessibility module (6/11) |  |
| 8 |  | Copyright? | Enhance DTP accessibility module (7/11) |  |
| 9 | Introduction to Sarah Parsons (autism) and Sarah Lewthwaite |  | Enhance DTP accessibility module (8/11) |  |
| 10 |  |  | Enhance DTP accessibility module (9/11) | Draft blogpost on what they have got from the experience. |
| 11 | Adding info to LinkedIn profiles and asking for recommendations |  | Enhance DTP accessibility module (10/11) | Finish blogpost |
| 12 |  |  | Enhance DTP accessibility module (11/11) | Give presentation to iSols and ADEs/DHoSE etc |

### Other professional development

- Any CoP sessions during their employment

- Sessions that X is running for interns.

- Is there anything relevant on FutureLearn Campus?

- AbilityNet webinars: https://abilitynet.org.uk/free-resources/webinars