## Gantt Chart
|  | 2xxx | [7 empty] | 2xxy | [13 empty] | 2xxz | [14 empty] | 2xyz
Numbered tasks | Nov |  | Dec | Jan | Feb | Mar | Apr | May | Jun |  | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr |  | May | Jun |  | Jul |  | Aug | Sep |  | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun |  | Jul | Aug | Sep | Oct | Nov | Dec
1. Initial literature review
2. Project rationale
3. Design investigation and identify resources available
4. Develop statistical skills
5. Carry out investigation
6. Learn how to use computer packages
7. Analyse data
8. Write report on investigation (6 month report)
9. Draft questionnaire and identify participants for pilot study
10. Finalise questionnaire identifying methods of statistical analysis
11. Identify target group and carry out pilot study
12. Analyse questionnaire and review pilot study
13. Nine month transfer report
14. Meeting with supervisor
15. Holidays
16. Redraft questionnaire for survey
17. Establishing target group and sampling approach for survey
18. Complete survey
19. Write report on findings (First draft of 18 month report)
20. Final draft of 18 month report
21. First draft of 24 month report, including second investigation
22. Final draft of 24 month report
23. Carry out further research and/or analysis
24. Prepare chapter headings and drafts
25. Complete and submit paper for conference (drafts and completed paper)
26. Job applications and interviews
27. Prepare second drafts of chapters
28. Complete and submit paper to journal
29. Complete and submit final draft of thesis
30. Prepare for Viva
[19 empty] | Key: |  | Reading/Planning/Analysis | [7 empty] | Holidays
[21 empty] | Job applications and interviews | [7 empty] | Thesis write-up/Viva
[21 empty] | Practical work |  |  |  |  | Floats |  |  | Milestone - report/paper submission